## Assumptions
Scale & Financial Assumptions
Kashyap Adhikari platform ¦ Version 0.1 ¦ 8 September 2026 ¦ Owner: Jyphra Technology Pvt. Ltd.
Assumption | Value | Unit / treatment | Minimum | Recommended | Enterprise
Model owner | Jyphra Technology Pvt. Ltd.
Delivery model | Jyphra-led hybrid team with externally contracted agency capacity
Development period | 12–15 months
Registered-user launch capacity | 100000 | users
Scale-without-redesign target | 500000 | users
Monthly active users baseline | 20000 | users
Daily active users baseline | 5000 | users
Normal peak concurrent users | 1000 | users
Support model | Business-hours monitoring and user support; emergency contact outside hours without 24/7 SLA
Cloud model | Managed critical services plus cost-efficient compute/containers
Contingency rate | 15% | applied to implementation subtotal
Illustrative VAT rate | 13% | shown separately; confirm tax treatment before contracting
USD/NPR planning rate | 151.48 | NRB selling rate on 2026-09-08
Planning horizon | 3 | post-launch operating years
Budget disclosure | Workstream/phase totals only; no individual compensation

## Implementation Budget
Implementation Budget by Workstream
All amounts NPR millions; consolidated totals intentionally avoid individual salary disclosure.
Workstream | Minimum | Recommended | Enterprise | Scope note
Product discovery, program governance and business analysis | 1.4 | 2.8 | 4.5 | Core delivery
UX research, UI design, accessibility and prototype | 1 | 2 | 3.2 | Core delivery
Android and iOS mobile applications | 3.4 | 6.2 | 9.5 | Core delivery
Backend APIs, database and integration services | 3.6 | 6.8 | 10.5 | Product capability
Web administration and moderation portal | 1.5 | 2.8 | 4.5 | Product capability
Genealogy graph, Nata/Saino and cultural-rule framework | 1.8 | 3.6 | 5.8 | Product capability
Chat, notifications, media and maps | 1.4 | 2.8 | 4.8 | Product capability
QA automation, devices, performance testing and UAT | 1.5 | 3.2 | 5.2 | Product capability
Security, privacy engineering and independent assessment | 0.8 | 2 | 3.8 | Assurance/platform
DevOps, environments, monitoring and release automation | 0.9 | 1.8 | 3 | Assurance/platform
Genealogy migration tooling and controlled pilot import | 1 | 2.2 | 3.8 | Assurance/platform
Training, store readiness, launch and stabilization | 0.7 | 1.5 | 2.5 | Launch readiness
Implementation subtotal | 19 | 37.7 | 61.1
Contingency (15%) | 2.85 | 5.655 | 9.165
Implementation incl. contingency, excl. VAT | 21.85 | 43.355 | 70.265
Illustrative VAT (13%) | 2.8405 | 5.6362 | 9.1344
Implementation incl. contingency and illustrative VAT | 24.6905 | 48.9912 | 79.3994

## Operating Costs
Three-Year Operating Cost Forecast
Amounts NPR millions; Year 1 begins after production launch.
Cost category | Min Y1 | Min Y2 | Min Y3 | Rec Y1 | Rec Y2 | Rec Y3 | Ent Y1 | Ent Y2 | Ent Y3
Cloud compute, managed database, cache and networking | 1.2 | 1.5 | 1.8 | 2.4 | 3 | 3.8 | 4.2 | 5.3 | 6.8
Object storage, backup and disaster recovery | 0.4 | 0.5 | 0.7 | 0.8 | 1 | 1.3 | 1.5 | 1.9 | 2.5
OTP, notification, email, maps and external APIs | 0.6 | 0.8 | 1 | 1.2 | 1.6 | 2.1 | 2.4 | 3.2 | 4.2
Application maintenance and enhancements | 2.4 | 2.8 | 3.3 | 4.8 | 5.5 | 6.4 | 8 | 9.2 | 10.8
Business-hours operations and user support | 1.4 | 1.7 | 2 | 2.8 | 3.3 | 3.9 | 4.8 | 5.6 | 6.6
Security, monitoring, audits and compliance | 0.6 | 0.8 | 1 | 1.4 | 1.7 | 2.1 | 2.8 | 3.4 | 4.2
Content, moderation and genealogy operations | 0.8 | 1 | 1.2 | 1.8 | 2.2 | 2.7 | 3.5 | 4.2 | 5
Licences, devices, training and administration | 0.4 | 0.5 | 0.6 | 0.8 | 1 | 1.2 | 1.4 | 1.7 | 2
Annual total | 7.8 | 9.6 | 11.6 | 16 | 19.3 | 23.5 | 28.6 | 34.5 | 42.1
Three-year total | Min Y1: 29; Rec Y1: 58.8; Ent Y1: 105.2

## TCO Summary
Three-Year Total Cost of Ownership
Decision view; NPR millions. Recommended is the approved planning baseline, not a vendor quotation.
Cost layer | Minimum professional | Recommended baseline | Enterprise strengthened
Implementation subtotal | 19 | 37.7 | 61.1
Implementation contingency | 2.85 | 5.655 | 9.165
Implementation incl. contingency, excl. VAT | 21.85 | 43.355 | 70.265
Three-year operations, excl. VAT | 29 | 58.8 | 105.2
Three-year TCO, excl. VAT | 50.85 | 102.155 | 175.465
Illustrative VAT if fully applicable | 6.6105 | 13.2802 | 22.8104
Three-year TCO incl. illustrative VAT | 57.4605 | 115.4352 | 198.2754
PLANNING RECOMMENDATION: Adopt the Recommended baseline. Release funds by gated phases; procure cloud/SMS/map services using live quotations; and reforecast quarterly against actual usage.

## Staffing Plan
Staffing and Delivery Capacity
No individual salary rates. Capacity is shown as indicative concurrent FTE ranges and sourcing model.
Capability | Primary source | Min low | Min high | Rec low | Rec high | Enterprise high
Executive sponsorship and product ownership | Jyphra | 1 | 2 | 1 | 2 | 2
Program management and business analysis | Jyphra-led hybrid | 2 | 3 | 3 | 4 | 6
UX/UI and accessibility | Hybrid | 1 | 2 | 2 | 3 | 4
Mobile engineering | Hybrid | 3 | 4 | 5 | 7 | 10
Backend/platform engineering | Hybrid | 3 | 4 | 5 | 7 | 11
Admin web engineering | Hybrid | 1 | 2 | 2 | 3 | 5
QA and test automation | Hybrid/independent | 2 | 3 | 3 | 5 | 7
DevOps/SRE and security | Hybrid/specialist | 1 | 2 | 2 | 3 | 5
Data migration/genealogy operations | Jyphra/community-led | 2 | 4 | 4 | 7 | 12
Content/localization/moderation preparation | Jyphra/community-led | 2 | 3 | 3 | 5 | 8
Indicative concurrent delivery capacity |  | 18 | 29 | 30 | 46 | 70

## Funding Gates
Phase Funding and Approval Gates
Percentages apply to the chosen implementation scenario before contingency and tax.
Gate | Phase | Share | Release evidence | Approval owner
G0 | Mobilization and validated backlog | 10% | Signed charter, governance, architecture decisions, executable backlog | Jyphra Product Owner + Sponsor
G1 | UX, architecture and foundations | 15% | Approved prototype, threat model, environments and CI/CD | Jyphra Product + Technology
G2 | Core identity and genealogy | 25% | Demonstrated core workflows, audit and migration pilot | Jyphra Product + Genealogy Authority
G3 | Community, chat and administration | 25% | Feature-complete test build and operational controls | Jyphra Product + QA
G4 | Hardening and UAT | 15% | Security/performance tests, UAT acceptance, store package | Jyphra Release Board
G5 | Launch and stabilization | 10% | Production launch, monitoring, handover and warranty entry | Jyphra Sponsor
Control | PASS — allocations equal 100%

## Sources & Notes
Sources, Limitations and Refresh Rules
External prices are volatile; validate quotations before procurement or contract signature.
Input | Value | As of | Source | URL | Use / limitation | Owner
USD/NPR selling rate | 151.48 NPR/USD | 2026-09-08 | Nepal Rastra Bank | https://www.nrb.org.np/forex/ | Official daily rate; model values are NPR | Jyphra Finance/Procurement
Firebase pricing | Pay-as-you-go / usage based | 2026-09-08 | Google Firebase | https://firebase.google.com/pricing | Use current calculator and Nepal SMS rate at procurement | Jyphra Finance/Procurement
AWS compute pricing | Usage and region dependent | 2026-09-08 | Amazon Web Services | https://aws.amazon.com/ec2/pricing/ | Hybrid-cloud benchmark; architecture is vendor-neutral | Jyphra Finance/Procurement
AWS managed database pricing | Usage and region dependent | 2026-09-08 | Amazon Web Services | https://aws.amazon.com/rds/pricing/ | Confirm selected region, HA, backups and transfer | Jyphra Finance/Procurement
Nepal software engineer compensation | Published range NPR 526k–1.397m annual; broad market signal only | 2026-09-08 | Levels.fyi | https://www.levels.fyi/t/software-engineer/locations/nepal | Not used to disclose individual rates | Jyphra Finance/Procurement
Nepal outsourcing benchmark | USD 20–40/hour indicative | 2026-09-08 | Bytecode Developers | https://bytecodedevelopers.com/blog/why-outsourcing-to-nepal-saves-big | Commercial source; triangulation only | Jyphra Finance/Procurement
VAT/tax treatment | 13% illustrative model assumption | 2026-09-08 | Jyphra planning assumption | https://ird.gov.np/ | Tax adviser must confirm taxable base, withholding and exemptions | Jyphra Finance/Procurement

## Checks
Model Checks
PASS means structural arithmetic controls reconcile; it does not convert estimates into supplier quotations.
Check | Result | Delta | Where to fix | Notes
Funding allocation equals 100% | PASS | 0 | Funding Gates | Must equal zero
Recommended TCO exceeds minimum | PASS |  | TCO Summary | Scenario ordering
Enterprise TCO exceeds recommended | PASS |  | TCO Summary | Scenario ordering
Contingency rate equals approved 15% | PASS |  | Assumptions | Approved decision
Planning horizon equals 3 years | PASS |  | Assumptions | Approved decision
MODEL STATUS | PASS